## Sheet1
CITS5206 UniCoders (Group 5206_3)
Minutes of Meeting 4 held on August 10, 2020 (Week 3a)
Present: Sumayyah Ahmad, Manpreet Kaur, Zhuojun Yang,
Hao Li, (Han) Yit Tsin Chooi , Kang Liu
Apologies:
Absent:
Meeting Started: 4:30pm
ACTION
1.1 | Share Project Understanding
- | Set up of Virtual Environment required before running Client's
code
- | Everyone faced difficulties in setting up Virtual Environment
Everyone will pick an alternative tools to set things up:
- | Anaconda + Jupyter Notebook | Hao
- | Visual Studio Code | Kang
- | Anaconda Powershell Prompt | Manpreet
- | Visual Studio Code | George
- | Anaconda + Jupyter Notebook | Han
Project is split into two teams:
- | Generation of Deformed Image Samples | Han & Hao
- | Measurement of 3D Deformation via DIC | Remaining
Members
- | Once Environment is set, test run and study the codes | Everyone
1.2 | Planning for Sprint 1
- | Github will be set for everyone to collaborate | Kang
- | Will be planned by 15th August | Han
1.3 | Allocation of Responsibilities
- | Will be set by 17th August | Everyone
1.4 | Dates of Meetings with Auditors in the future
- | 31st of August, 21st of September & 12th October
1.5 | Date of Next Meeting (with Mentor)
- | TBC | Han
Meeting Closed: 5:35pm