## Sheet1
CITS 5206 UniCoders (Group 5206_3)
Minutes of Meeting 8 held on August 31, 2020(week 6)
Present: Kang Liu, Zhuojun Yang, Hao Li, Manpreet Kaur
Sumayyah (Auditor)
Apologies:
Absent:
Meeting Started: 10:30 AM
ACTION
1 | Report to team members
- | Project timeline
- | Note down daily work on group Trello | All members
2 | Discuss technical issue running MATLAB multiIDIC
3 | Main scripts task allocation
- | Main script STEP 1 | Manpreet
- | Main script STEP 2 | Eddie
- | Main script STEP 3 | George
- | Main script STEP 4 | Hao
4 | Things to present and discuss on next meeting
- | Present outline of pseudo code
- | Discuss the procedure of code and the crossover of others
Meeting Closed: 11: 20 AM