## Sheet1
CITS 5206 UniCoders (Group 5206_3)
Minutes of Meeting 14 held on September 21, 2020 (week 9)
Present: Kang Liu, Zhuojun Yang, Hao Li, Manpreet Kaur
Ghulam Mubashar (client)
Apologies:
Absent:
Meeting Started: 10:30 AM
ACTION
1 | Beginning of Sprint_3
- | Explain the plan for Sprint 3 on project timeline
- | Intruduction of the Team Commnunication Platform
- | Product Manager tasks assigning.
2 | Sprint_3 task allocation
- | Step 2 2D-DIC coding in python | Eddie
- | Step 1 DLT parameter coding in python | Manpreet
- | Step4 pro-3D-DIC coding in python | Hao Li
- | Step 3 3D-DIC coding in Python | George
3 | Technical dicussion platform introduced. (Technical problems post and discussion on Trello)
4 | Scheduling the meeting time for the week 9 and study break
Meeting Closed: 11: 00 AM