## Sheet1
CITS 5206 UniCoders (Group 5206_3)
Minutes of Meeting 15 held on September 25, 2020 (week 9)
Present: Kang Liu, Zhuojun Yang, Hao Li, Manpreet Kaur
Ghulam Mubashar (client)
Apologies:
Absent:
Meeting Started: 9:00 AM
ACTION
1 | Report of the progress of Sprint_3
- | Report the progress of Sprint 3
- | Asking the mentor for the how to discuss the technical issues in real life
- | Asking the mentor for the advises for the testing and client involvement during the testing
2 | Sprint_3 task allocation
- | Step 2 2D-DIC coding in python | Eddie
- | Step 1 DLT parameter coding in python | Manpreet
- | Step4 pro-3D-DIC coding in python | Hao Li
- | Step 3 3D-DIC coding in Python | George
3 | Technical issues dicussion about a certain functions in 2D-DIC and DLT.
4 | Scheduling the meeting time for the week 9 and study break
Meeting Closed: 11: 00 AM